## Slide 1
SMCELJPA Board Meeting, March 13, 2020
Express Lanes Financial Projections

## Slide 2
PROJECT UPDATES
2018
2019
2020
2021
2022
100% PS&E
Sep 2019
Begin
Construction
Mar 2019
Begin Construction
March 2020
Begin Toll Systems Installation
Spring
2021
Open
Express Lanes
Late 2022
Caltrans Project
Approval (South and North)
Nov 2018
Substantial Construction Completed
Feb 2020
Express
Lane
Addition
HOV to
Express Lane
Conversion
Begin Toll Systems Installation
Spring 2020
Potential Open Express Lanes
Late 2021
North of
Whipple
VTA Toll System Installation Completed
Summer 2021
End Construction Spring 2022
Begin Toll Systems Testing
Summer 2022
JPA Formed July 2019
VTA Potential Open Express Lanes
Late 2021
Begin Toll
Systems
Testing
Spring 2021
VTA Civil Construction Completed
Summer 2020

## Slide 3
  WHY CONSIDER AN EARLY OPENING?
  Proof of concept
  Southern segment (~6 miles) opening is timed with the opening of VTA’s 101 Express Lanes Project (~8 miles), creating a total of 14 miles
  Early identification of issues
  WHY DECIDE NOW?
  Initiate and issue the necessary design and construction contract change orders (Civil and Transcore) to keep project on schedule
  Help to determine when the SM 101 EL Equity Study needs to be completed
  Begin timely public outreach
SINGLE OR DUAL OPENING

## Slide 4
  Benefits From Early Opening
  Potential for first year excess net revenues
  Ability to manage the lane more efficiently with increased person throughput
  Encourage travel mode shift earlier
  Test revenue projections with actual operation
  Goodwill with private sector partners
  Early market penetration of FasTrak® in the corridor
  Early issue identification for more cost-effective resolution
  Early mitigation of risks
  Early driver adoption
  Timed with opening with VTA’s Express Lanes
SINGLE OR DUAL OPENING

## Slide 5
SINGLE OR DUAL OPENING
  Possible Delays that Prevent Early Opening
  Contingent on VTA being able to open late 2021
  TransCore’s ability to meet the schedule requirement
  MTC’s ability to staff back office operations
  Required O&M agreements with Caltrans & BAIFA/Transcore not executed in time
  Risks From Early Opening
  Potential for first year loss
  Congestion reduction in the general purpose lanes may not be obvious
  Adverse early reaction to the conversion from 2+ HOV to 3+ HOV
  Potential for extended warranty cost

## Slide 6
 | 10 mph Shear Speed Constraint (In $M) | 20 mph Shear Speed Constraint (In $M)
Average Gross Revenue of TOM runs | $16.6 | $25.5
Post-processing adjustment range |  | 
Anticipated cheaters of the system | $0.8 - $1.7 | $1.3 - $2.6
Revenue loss due to HOV-only mode time periods | $0.8 - $3.3 | $1.3 - $5.1
Toll zone based tolling inefficiencies | $2.5 - $3.3 | $3.8 - $5.1
Subtotal | $4.1 - $8.3 | $6.4 - $12.8
Operations and Maintenance Costs | $6.8 - $8.7 | $7.0 - $9.0
Revenue ramp‐up loss | $0.4 - $0.5 | $0.6 - $0.7
Capital Costs For Early Opening Tasks | $3.9 | $3.9
Subtotal | $11.1 - $13.1 | $11.5 - $13.6
Approximate Annual Excess Net Revenue | $1.4 – ($4.8) | $7.6 – ($0.9)
Early Opening Annual Excess Net Revenue Estimates
FINANCIAL INVESTIGATIONS

## Slide 7
  Summary Findings / Staff Recommendation
  Financial investigations for an early opening indicate the potential for up to $7.6 M in excess net revenue or a loss of up to ($4.8 M)
  Strong qualitative benefits support an early opening and the risk of an operating loss is low compared to the opportunity for excess net revenue
    Proof of concept – early adoption of use
    Early identification of issues
    Timed with the opening of VTA’s express lanes
  Staff recommends SMCEL JPA approve a two-phase opening of the US101 express lanes, one to be timed with the opening of VTA’s express lanes in late 2021, and the latter one north of Whipple in late 2022.

## Slide 8
Questions?
  For more information on the project, visit 101express.com