## Slide 1
C/CAG Board Meeting September 9, 2021
Quarterly Project Update

## Slide 2
  Construction Progress
  Construction Spotlight
  Financial and Risk Status
  Public Outreach Activities
AGENDA

## Slide 3
  Construction Progress
  Construction Spotlight
  Financial and Risk Status
  Public Outreach Activities

## Slide 4
PROJECT LIMITS
Notes: The SM101 project includes building a new express lane on the northern half, and converting the existing HOV lane in the southern half.

## Slide 5
2020
2022
Begin Construction
March 2020
Begin Toll System
Installation
Summer 2021
Open Express Lanes
Late 2022
Express
Lane
Addition
HOV to
Express Lane
Conversion
Begin Toll System Installation
Fall 2020
Open Express Lanes
Late 2021
North of
Whipple
South of
Whipple
Begin Toll Systems Testing
Summer 2022
PROJECT SCHEDULE
Begin Toll Systems Testing
Summer 2021
2021
Notes: The northern and southern sections will both be built and launched at different times. On both sides though, there are 3 main tasks: construction, toll systems installation, and opening the lane.

## Slide 6
SUSTAINABILITY CERTIFICATION
“The project team worked diligently with the community to collaborate and find ways to address climate-change risks, enhance social equity, protect the natural environment, and ensure safety. The Envision Silver award provides ample proof that everyone involved went above and beyond to deliver a resilient, sustainable, and equitable civil infrastructure project.”
-Melissa Peneycad, ISI’s Managing Director
Notes: The northern and southern sections will both be built and launched at different times. On both sides though, there are 3 main tasks: construction, toll systems installation, and opening the lane.

## Slide 7
SOUTH CONTRACT WORK COMPLETED
South of Whipple
through July:
Completed installation of equipment on the northbound side
Installation of equipment on southbound side nearly complete

## Slide 8
UPCOMING WORK: August – October
South of Whipple:
Licensing of equipment in city rights of way
Testing of tolling equipment
Testing of toll system
Photo of testing on the I-880 corridor

## Slide 9
NORTH CONTRACT CONSTRUCTION BLOCKS

## Slide 10
NORTH CONTRACT WORK COMPLETED
  North of Whipple through July:
  $221.68M of $326M completed (68%) with 53% time elapsed
  Completed demolition of median barrier
  New median barrier complete in Block 4
  Median sign foundations complete in Block 4
  Completed median paving
  Installed new protective plates on underpass foundations at Hillsdale Boulevard and 3rd Avenue
  Capital Preventative Maintenance (CAPM) (roadway rehabilitation) paving substantially complete

## Slide 11
NORTH CONTRACT WORK ONGOING
Median Barrier Demolition

## Slide 12
NORTH CONTRACT WORK COMPLETED
Protective Plates at Hillsdale Boulevard Underpass

## Slide 13
NORTH CONTRACT WORK ONGOING
Median Paving

## Slide 14
UPCOMING WORK: August - October
North of Whipple:
Completion of Block 4 paving
Completion of sign foundations in Blocks 1, 2, and 3 Installation of lights and sign structures in Blocks 1 and 4
Installation of tolling equipment (TransCore)
Notes: For the “northern contract” or second phase, there will be work in Palo Alto on both the freeway and on City Streets (confirmed by contractor)

## Slide 15
  Construction Progress
  Construction Spotlight
  Financial and Risk Status
  Public Outreach Activities

## Slide 16
Paving Overview

## Slide 17
CAPM Paving

## Slide 18
CAPM Paving
Notes: Caltrans pavement rehabilitation project combined was with the express lanes project to improve the finished pavement product in the corridor
Scope work:
  Grind the pavement 3/10th foot
  Add back 2/10th foot
  Complete 1/10th foot
All lanes are being repaved, northbound and southbound, as well as ramp transitions (not the ramps themselves though)
This work is currently ongoing, and is anticipated to conclude in early August 2021
Limits: between Broadway and Produce Avenue

## Slide 19
Final Layer (1/10th Overlay) Limits

## Slide 20
Final Layer (1/10th Overlay)
Notes: Scope of work:
  Grind 1/10th foot of existing asphalt pavement
  Add an overlay of 1/10th foot asphalt pavement
In blocks 1, 2 and 3, this work will begin once concrete barrier work is complete. The anticipated start is in Spring 2022
This will begin after the CAPM paving. It is anticipated to begin in August 2021, and conclude in late 2022
There are weather-related restrictions on when this work can take place
Limits: over the entire width of the existing pavement from Whipple Avenue to just past the I-380 interchange

## Slide 21
NORTH CONTRACT WORK ONGOING
Roadway Rehabilitation (CAPM) Paving

## Slide 22
NORTH CONTRACT WORK ONGOING
Roadway Rehabilitation (CAPM) Paving

## Slide 23
NORTH CONTRACT WORK ONGOING
Roadway Rehabilitation (CAPM) Paving

## Slide 24
NORTH CONTRACT WORK ONGOING
Roadway Rehabilitation (CAPM) Paving

## Slide 25
NORTH CONTRACT WORK ONGOING
Sponsorship Sign

## Slide 26
  Construction Progress
  Construction Spotlight
  Financial and Risk Status
  Public Outreach Activities

## Slide 27
CURRENT COST ESTIMATE - CONTRACT FOCUSED
(1) Estimated Cost represents current estimated cost to complete each contract.
(2) Expenditures include $12M deposit against North Contract – Civil.
(3) Percent completes shown are based on qualitative assessment of physical % complete per milestones and schedule.
(4) Å = Within budget, Å = identified potential risks that may significantly exceed budget if not mitigated, Å = Known impacts to budget - changes forthcoming.
Assume 100% utilization of Project Contingency in overall estimated cost of project
Percent of Project Contingency utilized to date

## Slide 28
CURRENT CONTINGENCY USAGE & BALANCE – CONSTRUCTION PHASE
Contingency expended includes the following:
  New contract change orders for various reasons including, barrier foundation revisions, grade revisions, maintenance of landscape areas, and misc. signage issues
  Contract bid item overruns
$0.19

## Slide 29
16.53
15.35
10.89
10.24
16.53
15.35
10.89
7.46
24.53
22.26
24.11
28.80
22.26
15.35
24.11
28.80
30.03
10.89
7.46
6.23

## Slide 30
Does not include risk associated with potential new median barrier impacts. Will be assessed and added to the risk register in the next week.

## Slide 31
  Construction Progress
  Construction Spotlight
  Financial and Risk Status
  Public Outreach Activities

## Slide 32
WEBSITE STATISTICS FOR 2021
Chart: 101express.com Pageviews (Jan 2021 - Jun 2021)
| 44197 | 44228 | 44256 | 44307 | 44337 | 44368
All | 2457 | 2948 | 3516 | 3651 | 3959 | 3826
Construction Update | 1024 | 1300 | 1415 | 1384 | 1562 | 1338
Main Site | 759 | 722 | 1208 | 1214 | 1340 | 1309
FAQ | 209 | 276 | 139 | 317 | 421 | 531

## Slide 33
PUBLIC INFORMATION – RECENT EFFORTS
  Recent highlights in the quarterly update:
  Adjusted nighttime working hours due to increased traffic volumes
  Ongoing and upcoming repaving work
Notes: Weekly construction information, including ramp closure details, emailed to those signed up on the project email list and posted to website
Ramp closure notification posted on ramps up to two weeks in advance of closures
Quarterly “newsletter” distributed via email to Elected Officials, City Officials, etc.
Focused information to cities/jurisdictions to distribute as requested

## Slide 34
  Redesigned Weekly Email Update
  More photos
  Explanation of work by roadway section
  More context to connect weekly work with the overall project plan
PUBLIC INFORMATION – RECENT EFFORTS
Notes: Weekly construction information, including ramp closure details, emailed to those signed up on the project email list and posted to website
Ramp closure notification posted on ramps up to two weeks in advance of closures
Quarterly “newsletter” distributed via email to Elected Officials, City Officials, etc.
Focused information to cities/jurisdictions to distribute as requested

## Slide 35
PUBLIC INFORMATION – UPCOMING EFFORTS
  Upcoming Public Information Efforts:
  Turning attention to the opening of the lanes
  Developing robust communications in coordination with VTA and MTC
  Continuing to communicate construction details
  Integrating outreach for construction and express lane opening
Notes: Weekly construction information, including ramp closure details, emailed to those signed up on the project email list and posted to website
Ramp closure notification posted on ramps up to two weeks in advance of closures
Quarterly “newsletter” distributed via email to Elected Officials, City Officials, etc.
Focused information to cities/jurisdictions to distribute as requested

## Slide 36
PUBLIC INFORMATION OVERVIEW
  Visitors can sign up for updates, contact Caltrans to ask a question, and view project status.
  To sign up for weekly or quarterly updates, email with the subject line 'Weekly' or 'Quarterly' to 101express@dot.ca.gov. Follow @CaltransD4 on Twitter for Project updates.
  101Express.com
Notes: Weekly construction information, including ramp closure details, emailed to those signed up on the project email list and posted to website
Ramp closure notification posted on ramps up to two weeks in advance of closures
Quarterly “newsletter” distributed via email to Elected Officials, City Officials, etc.
Focused information to cities/jurisdictions to distribute as requested

## Slide 37
Questions?