## Slide 1
C/CAG Board of Directors Meeting February 9, 2023
Quarterly Project Update

## Slide 2
  Project Progress
  Financial and Risk Status
  Communications Activities
AGENDA

## Slide 3
  Project Progress
  Financial and Risk Status
  Communications Activities

## Slide 4
PROJECT LIMITS
Operating Express Lanes
Begin Tolling Soon
Notes: The SM101 project includes building a new express lane on the northern half and converting the existing HOV lane in the southern half.

## Slide 5
NORTH CONTRACT WORK COMPLETED
  Kiewit work north of Whipple Avenue through January 2023:
  Civil contract work 100% complete
  Proposed final cost: $350M out of $351.5M
  TransCore work north of Whipple Avenue through January 2023:
  Equipment installation, fiber splicing operation, and site commission testing 100% complete
  Most recent milestone cost (September): $20M out of $28.6M

## Slide 6
EXPRESS LANE OPERATING IN HOV 3+ ONLY MODE
CURRENT OPERATIONS

## Slide 7
North of Broadway:
North of Whipple Ave:
Step 1
Step 2
Step 3
Step 1
CONTRACT PAVEMENT WORK
Notes: Note that emergency repairs will attempt to fix structural section and that future projects currently programmed will repair pavement south of Broadway.

## Slide 8
POTHOLE REPAIRS

## Slide 9
TYPICAL ROADWAY SECTION
Excessive rain has caused washout of the base, which causes potholes

## Slide 10
CURRENT END OF PROJECT SCHEDULE
*Schedule includes weather dependent activities and corridor testing uncertainty
Notes: Other activities include closeout activities for Transcore, a toll commencement event, and the CTC vote to approve the highway planting funding.

## Slide 11
  Project Progress
  Financial and Risk Status
  Communications Activities

## Slide 12
CURRENT COST ESTIMATE - CONTRACT FOCUSED
(1) Estimated Cost represents current estimated cost to complete each contract.
(2) Expenditures exclude deposit against North Contract – Civil.
(3) Percent completes shown are based on qualitative assessment of physical % complete per milestones and schedule.
(4) Å = Within budget, Å = identified potential risks that may significantly exceed budget if not mitigated, Å = Known impacts to budget - changes forthcoming.

## Slide 13
CONSTRUCTION CONTINGENCY BALANCES
Contract change orders for various reasons including, k-rail salvage, barrier foundation revisions, grade and drainage revisions, maintenance of landscape areas, signage issues, and pavement corrections.

## Slide 14
3.32
10.32

## Slide 16
  Construction Progress
  Financial and Risk Status
  Communications Activities

## Slide 17
START OF TOLLING OUTREACH
  Awareness Campaign – 4 weeks before tolling begins
    Earned Media: Press Release, News Communications
    Website and Social Media Messaging
    Communication to Commute.org/TDMs, CBOs and cities
  Advertising Campaign – 2 weeks before and after tolling begins
    Billboards along 101 corridor (digital)
    Terrestrial Radio (traffic, news, sports, entertainment)
    Gas Station Ads
    Multi-lingual media (Univision, News for Chinese)
Notes: TDM – Transportation Demand Management Agencies, CBO – Community based organizations
This is the same information that Robert Casumbal presented to the SMCTA BOD on 1/13

## Slide 18
COMING SOON!
SAN MATEO - US 101 EXPRESS LANES PROJECT
Opening Event

## Slide 19
Questions?

## Slide 20
HIGHWAY PLANTING SCHEDULE
Notes: Pictured Left to Right - Ray Hartman Wild Lilac, Dwarf Coyote Brush, New Zealand Tea Tree, Pride of Madeira